## Slide 1
MARKET-ENTRY RECOMMENDATION
Prioritize Coastal and North for the first expansion wave
Attractiveness and ability to win point to two markets; Central remains a gated option.
BUILD SELECTIVELY
PRIORITIZE
DEPRIORITIZE
PARTNER / TEST
Coastal
81
North
78
Central
72
West
58
Market attractiveness →
Ability to win →
Recommendation
WAVE 1
1
Launch Coastal
Fastest growth; protect economics with a partner-led model.
2
Scale North
Strong fit and lower execution complexity support direct entry.
3
Gate Central
Run a 90-day commercial test before committing fixed cost.
Illustrative scoring only. Replace with sourced market, customer, and economics evidence.

## Slide 2
VALUE-CREATION ROADMAP
Sequence quick wins before scaling the operating model
The first 90 days validate economics and owners; later waves scale only after explicit gates.
0–30 DAYS
Mobilize
31–90 DAYS
Prove
3–12 MONTHS
Scale
Commercial
CCO
Segment accounts
and set price floors
Pilot value pricing
in two regions
Roll winning offers
across channels
Operations
COO
Baseline service cost
and bottlenecks
Redesign dispatch
and capacity rules
Automate repeatable
workflow steps
Organization
CHRO
Name initiative owners
and decision rights
Install weekly value
review cadence
Tie incentives to
realized value
Data & tech
CIO
Define KPI dictionary
and source systems
Ship executive cockpit
and QA controls
Scale governed data
products and alerts
Baseline signed off
Pilot economics proven
Scale funding released
Governance principle: fund the next wave only after the prior gate has an owner, evidence, and realized-value check.

## Slide 3
ILLUSTRATIVE VALUE CASE
$24M of annualized EBITDA potential is concentrated in three levers
Pricing, route density, and procurement contribute 75% of the modeled opportunity.
Value lever | EBITDA impact | Confidence | Accountable owner
Value pricing | $7M | Medium | CCO
Route density | $6M | High | COO
Strategic sourcing | $5M | High | CPO
Sales productivity | $4M | Medium | CCO
Back-office automation | $2M | Low | CIO
Annualized EBITDA potential (USD millions)
Chart: 
| Pricing | Routing | Sourcing | Sales force | Automation
Impact | 7 | 6 | 5 | 4 | 2
Recommendation: mobilize the top three levers now; keep the remaining $6M as gated upside until pilots validate adoption and run-rate cost.
MODEL BASIS
Fictional case • illustrative values • no client data
The table preserves exact modeled values; the chart communicates relative magnitude. Validate assumptions before any real decision.